# THE PRACTICE GROUNDS — PHASE 1 EXECUTION PLAN

## Design & Evidence: July 13 – August 28, 2026 (+ September class study)

Prepared for: Doug Smith

Version: 1.0 — July 12, 2026

Governing document: PRACTICE_GROUNDS_REPORT.md v0.2 (this plan executes its §9 Phase 1)

Operating assumptions: Doug at 10+ hours/week, working deep in the design; AI-assisted build in Cowork sessions on the MacBook Pro (creative development, per the Two-Machine Doctrine); two-stage validation — an August pilot with summer recruits, then a September study in Doug's classes.

## 1. Purpose and the One-Sentence Test

Phase 1 exists to answer one question with evidence rather than enthusiasm: does the merged Wall–Compass foundation produce real, transferring learning that real students voluntarily return to?

Everything in this plan serves that question. The phase produces eight artifacts (the design specs, the prototype, and the study), but its true output is a go/no-go decision on August 28 backed by data from actual learners — and a second confirmation from Doug's own classes in September before any public launch is finalized.

The discipline this plan holds throughout, inherited from the v0.2 revision: this is a design-and-evidence phase, never a paper phase. The playable prototype v2 is built inside it, as the study's test instrument. The hard end date is real. Specs freeze at the end of Week 2; everything discovered after that goes to a backlog, not into scope.

## 2. Calendar at a Glance

| Week | Dates | Focus | Milestone (Friday) |
| --- | --- | --- | --- |
| 1 | Jul 13–17 | Foundations: competency map, evidence schema, name, inventory | Name decided; schemas v0.1 approved |
| 2 | Jul 20–24 | Design specs: curriculum, mastery blueprint, baselines | Spec freeze (+ optional external re-review) |
| 3 | Jul 27–31 | Build I: engine, audio, Compass & Wall rounds, logging | Playable core loop in Doug's hands |
| 4 | Aug 3–7 | Build II: notation Build, Inspections, Loom v0, a11y, voice pass | Pilot-ready build; dry run with 2 friendlies |
| 5 | Aug 10–14 | Pilot week one (participants play daily) | Mid-pilot check-in; hotfixes only |
| 6 | Aug 17–21 | Pilot week two | Play period ends Sun Aug 23 |
| 7 | Aug 24–28 | Closeout: analysis, exit interviews, report v0.3 | Go/no-go decision — Aug 28 |
| — | Sep 8–25 | Class study (first weeks of term) | Confirmation gate before public MVP launch |

If GO on August 28: Phase 2 (public MVP build) begins September 1 in parallel with class-study preparation, with the September results as the final gate on launch, not on build.

## 3. Operating Rhythm

Weekly cadence (fits 10+ hours without sprawl):

•  Monday — planning session (Cowork, ~1 hr): review last week's milestone, set the week's targets, resolve open decisions. Ends with an updated DECISIONS.md.

•  Midweek — working session (Cowork, 2–3 hrs): the week's main co-design or build-review work. During Weeks 3–4 this is Doug playing the latest build with the builder present.

•  Friday — milestone session (~1–2 hrs): milestone check against this plan, playtest, voice pass on any new UI text, Cowork log entry, handoff written.

•  Doug's independent time: curriculum thinking, voice drafting, recruiting, and playing builds between sessions.

Ground rules (from vault doctrine and the v0.2 report): all work on the MacBook Pro; git status/pull before, review/commit after each session, one bounded task per commit; markdown-first, .docx renders on demand only; every session logs to Cowork_log_file.md and multi-session work leaves a handoff; Whisperer text is drafted against the Voice Dossier and every line passes through Doug before it ships to a student.

Workspace layout (created now):

_DEV_INCUBATOR/PRACTICE_GROUNDS/

PRACTICE_GROUNDS_REPORT.md        ← governing doc (v0.2)

PHASE1_EXECUTION_PLAN.md          ← this plan

DECISIONS.md                      ← running decision log

the_wall_prototype.html           ← v1 sketch (historical)

01_SPECS/                         ← Weeks 1–2 outputs

02_PROTOTYPE_V2/                  ← Weeks 3–4 build

03_STUDY/                         ← protocol, consents, data, analysis

## 4. Week-by-Week Detail

### Week 1 (Jul 13–17) — Foundations

W1.1 — Suite name decision. (Doug decides; Monday–Friday window.) Shortlist from the report: The Practice Grounds, The Guildhall, The Workshop, The Yard — plus anything the week suggests. Criteria: says what it is to a stranger, lives comfortably inside the city-wall world, survives being said aloud on a podcast. Decision recorded in DECISIONS.md; the domain/subdomain choice (e.g., play.thecommontone.com) rides along with it.

W1.2 — Competency map v0.1. (Claude drafts, Doug reviews as the theorist; the phase's keystone artifact.) Scope for Phase 1: the interval domain (12 interval classes × direction × melodic/harmonic × out-of-key/in-key) and the degree domain (major diatonic degrees, then the first chromatics; minor deferred to MVP). Each competency gets a stable ID, prerequisites, and transfer targets (register, key, timbre, presentation). Format: YAML in 01_SPECS/COMPETENCY_MAP_v0.1.yaml with a companion prose spec. Deliberately minimal and versioned — it grows from evidence, not ambition.

W1.3 — Learning-evidence schema v0.1. (Claude drafts, Doug reviews.) The record written for every single response: competency ID, stimulus conditions (root, key context or none, register, timbre, direction), scaffolds active (hints, resolution playback, narrowed options, replay count), input method, response, correctness, latency, and session position. This schema is the "learning contract" made concrete — everything the pilot analysis needs must be captured here, so it is reviewed against the study protocol (W2.6) before freeze.

W1.4 — Interactive-accessories inventory. (Doug points to where they live; Claude catalogs.) Circle of Fifths, Sonic Explorer, CT Quiz, Crosswords, Blues Progression Builder, and the visual tools — each mapped against the competency map: reusable capability, Explore-door candidate, content source, or not relevant to Phase 1. Output: 01_SPECS/ACCESSORIES_INVENTORY.md.

W1.5 — Voice foundations. (Doug-led.) A short UI-voice guideline distilled from the Voice Dossier: how the Craftsman coaches in ten words, what Krankenhorn says at a pass and at a fail, where the Jester is allowed, and the dosage rules (brief, optional, pedagogically triggered). This exists so Weeks 3–4 draft against a standard instead of inventing one under deadline.

Friday milestone: name decided; competency map and evidence schema approved at v0.1; inventory done; voice guideline drafted.

### Week 2 (Jul 20–24) — Design Specs, then Freeze

W2.1 — Merged curriculum v2. (Both — the week's biggest item, and the most Doug-shaped.) The unified Wall–Compass ladder: Compass staging (cadence → probe → resolution; lower tetrachord → upper → octave → first chromatics), Wall staging (contrast pairs, blocked-then-interleaved), the session-composition rules (how a daily session mixes Compass rounds, Wall rounds, Build sets, and Loom reviews), the cross-gating rules (neither view runs more than one region ahead of the other), the in-key merge points, and the scaffold-fading rules keyed to learner state rather than level number. Output: 01_SPECS/CURRICULUM_V2.md.

W2.2 — Mastery & Seal blueprint. (Claude drafts from report §6.1; Doug approves the criteria.) For each Phase-1 rank: the exact competency coverage an Inspection guarantees, sample counts per competency (weakest items oversampled), accuracy and latency criteria, the retention check (Loom-verified, not exam-day), the transfer conditions rotated, and the unscaffolded requirement. Output: 01_SPECS/MASTERY_BLUEPRINT.md — this doubles as the published-syllabus source later.

W2.3 — Game-mechanics matrix. (Claude drafts.) Every activity in prototype v2 classified by learner action (recognize / produce / construct / repair) and by view (Wall/Compass), verifying genuine variety — the anti-same-skeleton check. Anything scoring "recognize-only" across a whole session gets redesigned now, not after the pilot.

W2.4 — Accessibility & consent baseline. (Claude drafts; Doug approves.) The acceptance checklist from report §8.5 turned into testable items (keyboard paths, focus order, live regions, non-color cues, reduced motion, type/contrast); the pilot consent forms (adults; parental consent template for any minors); the three-consent account model documented for Phase 3. Note for the record: the full minors/privacy legal review is a pre-launch item (Phase 2/3), not a pilot item — the pilot uses direct, informed, personal consent.

W2.5 — Repertoire-bridge design sketch. (Claude drafts.) Not built in Phase 1 — designed for. Which CTSF fields the item generator will need, what a repertoire-sourced question looks like for intervals/degrees, and what this implies for Repertoire entries (feeds the repertoire-enrichment pipeline later). Output: 01_SPECS/REPERTOIRE_BRIDGE_SKETCH.md.

W2.6 — Study protocol v1. (Both.) Full pilot protocol — see §5 below — cross-checked against the evidence schema: every analysis planned must be computable from records the prototype actually writes.

Friday milestone — SPEC FREEZE. The six specs are frozen for the build. Optional but recommended: send the spec pack out for a short external re-review (the July 12 reviewer is the natural choice) with a 1-week window, feedback landing during build Week 3 — blueprint and curriculum adjustments are cheap until about July 31.

### Weeks 3–4 (Jul 27 – Aug 7) — Build Prototype v2

(Claude builds in Cowork sessions; Doug plays every build, midweek and Friday, and runs the voice pass. The v1 prototype is reference, not foundation — v2 is a fresh build against the schemas.)

Week 3 — the core loop:

•  Project scaffold: Vite + TypeScript, tonal (music logic), smplr sampled piano + one alternate timbre, VexFlow 5 present from day one.

•  Cancellable audio scheduler with explicit playback state — first thing built, everything else uses it.

•  Compass rounds: cadence establishes key → probe note → answer (degree number / movable-do / piano key) → audible stepwise resolution, win or lose.

•  Wall rounds: melodic intervals, out-of-key and in-key variants, contrast-pair introduction, interleaving engine.

•  Evidence logging to the W1.3 schema from the very first playable question — localStorage plus a minimal sync (one Supabase table, pilot-only) so study data arrives without asking participants to export files.

•  Session conductor v0: composes the daily ~10-minute session per the curriculum's composition rules.

Week 4 — assessment, access, and voice:

•  Notation-based Build mode: place the note on a VexFlow staff, spelling assessed (m3 ≠ A2), key-context aware.

•  Blueprint Inspection engine per W2.2 — coverage-guaranteed, scaffolds off, conditions rotated.

•  Loom v0: within-pilot spaced review (day-scale scheduling is enough for a 14-day study).

•  Scaffold tracking and state-based fading, wired into the evidence records.

•  Accessibility baseline implemented and tested against the W2.4 checklist (keyboard-only run-through; screen-reader spot check; reduced-motion; non-color cues).

•  In-app instruments for the study: day-1 and day-14 assessment mode (see §5), one-tap post-session enjoyment probe (~3 times/week), fully skippable.

•  Onboarding flow and the voice pass: Doug passes every student-facing string against the W1.5 guideline.

•  Cross-device test: macOS Safari/Chrome, iPad, one Android phone; iOS audio unlock and mute-switch handling verified.

•  Dry run (Aug 6–7): two friendly non-participants play three days compressed into two; every discovered issue is triaged as hotfix-now or backlog.

Scope fence for the build — cut in this order if time presses, never cutting below the line: Explore sandbox → second timbre → MIDI input → cosmetic wall animation. Never cut: evidence logging, the Inspection engine, accessibility baseline, the resolution playback, the voice pass.

### Weeks 5–6 (Aug 10–23) — The Pilot

Participants play ~10 minutes daily for 14 days. Doug is the human presence: a personal welcome message, a mid-pilot check-in (Aug 14–15), and availability for stuck participants. Engineering enters hotfix-only mode — no feature changes mid-study, so the data means something.

### Week 7 (Aug 24–28) — Closeout

Analysis against the §6 criteria (Claude computes, both interpret); exit interviews with 5–8 participants (Doug, 15 minutes each — what they'd say to a friend about it, where it felt like drill, where it felt like music); report updated to v0.3 with results; go/no-go decision Friday, August 28, recorded with reasons in DECISIONS.md.

## 5. The Learner Study, Precisely

### 5.1 August pilot

•  Who: 8–15 completers; recruit 14–20 against summer attrition. Doug's network: private students, adult learners, the online community, colleagues and their families. Three strata, at least two people each: true beginners (can't name an interval), some-theory (a year or two of lessons/band), and experienced-but-untrained-ears.

•  Consent: written informed consent; adults preferred; minors only with parental consent and Doug's direct relationship to the family. Data collected is pseudonymous (participant code, no names in the dataset).

•  Protocol: Day 1 — onboarding + baseline assessment (~10 min). Days 1–14 — daily session (~10 min; the Candle's five-minute bar applies). Day 14 (window: days 13–15) — closing assessment, same form as baseline. Then exit survey; interviews for a subset.

•  The assessment instrument (same at both ends, ~10 minutes, in-app): trained items under trained conditions; transfer probes — same competencies at novel register and the untrained timbre; context probes — degree identification with a cadence the participant hasn't drilled with; and two or three real-music micro-probes (short recorded excerpts: "which interval opens this melody?") as an honest, hard test of ecological transfer. Baseline scores also give each stratum its starting map.

•  Measured throughout (from the evidence stream, no extra burden): daily return without prompting, session lengths, per-competency learning curves, scaffold-fade trajectories, gate-stuck events, enjoyment probes.

### 5.2 September class study (confirmation gate)

First two full weeks of term (target Sep 8–25 including setup): the same instrument and protocol inside Doug's own classes, larger N (~20–40), parental consent flow prepared in Week 2, participation never graded. Purpose: confirm the August result with representative students, catch classroom-context failures (devices, headphones, attention economics), and produce the evidence base the public syllabus will cite. The September study gates the public launch; the August pilot gates the MVP build — so a GO in August means Phase 2 construction proceeds through September at no calendar cost.

## 6. Go/No-Go Criteria (decided now, before any data exists)

GO requires all four:

1.  Voluntary return: ≥60% of participants complete ≥10 of 14 days without individual prompting beyond the app's own reminders.

2.  Learning: clear pre→post gains on trained competencies for a majority in every stratum, and positive transfer — gains on novel-register/novel-timbre probes of at least half the trained-item gain. (Trained-only gains with zero transfer = the Jakoby failure mode; that's a REVISE, not a GO.)

3.  Experience: median enjoyment ≥4/5; in exit interviews, a majority describe it unprompted as something they intend to continue.

4.  System: the evidence schema answered every analysis question without redesign; no unresolved accessibility blocker for any pilot participant; no gate held a motivated participant stuck >3 days.

REVISE (the likely honest outcome in some degree): specific criteria missed for identifiable, fixable reasons → a scoped two-week revision loop, with the September class study absorbing the re-test. NO-GO: learning or return fails broadly across strata → the concept goes back to first principles with the pilot data as the inheritance; the sunk cost is six weeks, which is precisely why the phase is shaped this way.

## 7. Roles

Doug — decides: name, curriculum shape, mastery criteria, voice, go/no-go. Owns: recruiting and every human relationship in the study, the voice pass, the theorist's review of competency map and curriculum, exit interviews. With 10+ hours/week, Doug additionally co-designs the curriculum in working sessions rather than reviewing it after the fact — the single highest-leverage use of his time — and, if the hours are there in Weeks 3–4, drafts the why interval drilling alone fails Substack essay while the pedagogy is hot (it becomes the launch manifesto in Phase 2).

Claude (Cowork sessions) — drafts all specs, builds prototype v2, instruments the study, computes the analysis, keeps the logs, writes the handoffs, maintains DECISIONS.md.

External reviewer (optional, recommended) — one-week re-review of the frozen spec pack at end of Week 2; invited back for the v0.3 results report.

## 8. Risk Register (Phase-1-specific)

| Risk | Likelihood | Mitigation |
| --- | --- | --- |
| Recruiting shortfall in mid-summer | Medium-high | Recruit 2× target starting Week 1 (not Week 4); adults welcome; Doug's personal ask converts far better than a signup page |
| Pilot attrition | Medium | Five-minute daily bar; Candle-with-forgiveness in v2; Doug's mid-pilot personal check-in; count partial completers in analysis honestly |
| Build slips past Aug 7 | Medium | The scope fence (§4, Weeks 3–4); dry-run date immovable; if truly forced, the pilot start slides ≤1 week and closeout compresses — the Aug 28 decision date holds |
| Spec churn after freeze | Medium | Freeze is real; a BACKLOG.md catches every good idea; only the external re-review can reopen a spec, and only in Week 3 |
| Students prefer their scaffolds and blocked practice (predicted by the research) | High — and it's a test condition, not a bug | The in-world explanations ("mixed rounds feel harder because they're working") are themselves under study; exit interviews probe whether they landed |
| Evidence sync fails silently mid-pilot | Low | localStorage is the primary record with sync as transport; daily automated completeness check on the study table; dry run validates end-to-end |
| Doug's 10 hours get eaten by other Common Tone fronts | Medium | The three fixed weekly sessions are the protected core (~5 hrs); everything else flexes; Monday session re-scopes the week honestly |

## 9. Standing Decisions and Open Decisions

Decided (recorded in DECISIONS.md): both-tiered audience; fully in-world branding at pedagogical dosage; freemium with three separate consents; merged Wall–Compass foundation; learning contract over shared engine; blueprint mastery; pilot-then-class-study validation; Doug at 10+ hrs/week.

Open, with owners and dates: suite name (Doug, by Jul 17); domain/subdomain (Doug, by Jul 24 — needed only for Phase 2, decided early because the name informs it); external re-review yes/no (Doug, by Jul 24); September study exact dates (Doug, once term schedule is known).

## 10. What Happens Immediately

Doug, this week (by Jul 17):

1.  Sit with the name shortlist; decide or ask for more candidates.

2.  Point the next session at where the interactive accessories live (repo/folder/URLs) for the inventory.

3.  Start the recruiting list — names, strata, how you'll ask. Target 14–20 asks.

4.  Read the competency map and evidence schema drafts when they land (early week) — your corrections there propagate through everything downstream.

5.  One hour with the Voice Dossier and the W1.5 guideline draft.

Next Cowork session (Monday Jul 13):

1.  Draft COMPETENCY_MAP_v0.1.yaml + spec.

2.  Draft EVIDENCE_SCHEMA_v0.1.md.

3.  Seed 01_SPECS/, 02_PROTOTYPE_V2/, 03_STUDY/, BACKLOG.md in the workspace (folder scaffolding and DECISIONS.md are created with this plan).

4.  Draft the name-decision one-pager (criteria + shortlist pros/cons) so the decision takes Doug twenty minutes, not a week.

Plan prepared July 12, 2026 (Cowork session), executing PRACTICE_GROUNDS_REPORT.md v0.2 §9 Phase 1. This document is the working checklist for the next seven weeks; `DECISIONS.md` is its running memory; the Friday milestone sessions are its heartbeat.

A note from the bench This plan is a working checklist, not literature. The Monday session re-scopes each week honestly; the Friday session checks the milestone; DECISIONS.md remembers why. If a week ends and the milestone line in §2 isn't true, that goes in the log too — the plan bends before it lies.